## Bid Workflow Hierarchy
BIP BID & PURSUIT LIFECYCLE — MASTER WORKFLOW HIERARCHY ¦ Emergency Services · Defence · Justice ¦ £50m – £1.5bn
Phase | L1 Stage # | L1 Stage | L2 Sub-Process | L3 Task | Responsible Role | Accountable | Consulted | Informed | Inputs | Outputs / Deliverables | Decision Gate / QC | Effort | Type | Notes / Ref
CAPTURE PHASE | C1 | Customer Requirement Identified | Intelligence Gathering & Market Scanning | Monitor OJEU/Find-a-Tender for relevant procurement notices | Capture Lead | Bid Director | Market Intelligence Team | Bid Board | Market scan tools, sector intel reports, client relationship data | Long-list of target opportunities, opportunity log entry | Opportunity Screening Go/No-Go Gate | Low | Sequential | Shipley Phase 1
CAPTURE PHASE | C1 | Customer Requirement Identified | Intelligence Gathering & Market Scanning | Conduct stakeholder listening exercises with client contacts | Capture Lead | Bid Director | Account Manager | Commercial Lead | Existing relationship map, client org chart | Intelligence notes, relationship map update |  | Low | Parallel
CAPTURE PHASE | C1 | Customer Requirement Identified | Intelligence Gathering & Market Scanning | Review customer strategic plans, spending reviews & published strategies | Market Intelligence Analyst | Capture Lead | SME | Bid Director | Published government/client strategy documents | Customer insight summary, hot spots register |  | Low | Sequential
CAPTURE PHASE | C1 | Customer Requirement Identified | Customer Needs Analysis | Identify and map key stakeholders within the buying authority (DMU) | Capture Lead | Bid Director | Account Manager | Bid Manager | Org chart, previous bid history, relationship CRM data | Stakeholder/power map, DMU register |  | Medium | Sequential | PFC Slide 14
CAPTURE PHASE | C1 | Customer Requirement Identified | Customer Needs Analysis | Conduct structured interviews with key decision makers | Account Manager | Bid Director | Capture Lead | Commercial Lead | Stakeholder map, approved engagement plan | Interview notes, buyer values assessment |  | Medium | Iterative | PFC Slide 24
CAPTURE PHASE | C1 | Customer Requirement Identified | Customer Needs Analysis | Document and validate buyer values and evaluation criteria | Capture Lead | Bid Director | Solution Architect | Commercial Lead | Interview outputs, ITN/OJEU notice | Buyer values register, weightings matrix | Buyer Values Sign-off Gate | Medium | Sequential | PFC Slide 24
CAPTURE PHASE | C2 | Opportunity Pipeline | Opportunity Qualification (DQC) | Complete Deal Qualification Checklist (DQC) covering attractiveness, deliverability, risk & win likelihood | Bid Director | Senior Responsible Industry Exec | Commercial Lead / SME | Bid Board | Opportunity brief, buyer values, market intel, resource forecast | DQC completed artefact, pursue/no pursue recommendation | FORMAL BID BOARD PURSUE DECISION | High | Sequential | PFC Slide 20; APMP Bid Decision
CAPTURE PHASE | C2 | Opportunity Pipeline | Opportunity Qualification (DQC) | Assess strategic fit against BIP sector portfolio and growth plan | Bid Director | Partner | Capture Lead | Account Manager | BIP strategic plan, sector pipeline data | Strategic fit assessment, risk-adjusted pipeline entry |  | Medium | Sequential
CAPTURE PHASE | C2 | Opportunity Pipeline | Win Probability (PWIN) Assessment | Score opportunity against competitive position, relationships and solution readiness | Bid Director | Partner | Capture Lead / Commercial Lead | Bid Manager | DQC output, competitive intelligence, stakeholder map | PWIN score (%), PWIN rationale note |  | Medium | Iterative | PWIN Architect framework
CAPTURE PHASE | C2 | Opportunity Pipeline | Win Probability (PWIN) Assessment | Identify win themes and preliminary differentiators vs likely competitors | Capture Lead | Bid Director | Solution Architect | Commercial Lead | Competitive landscape map, buyer values | Draft win themes register (3-5 themes) |  | Medium | Sequential | PFC Slide 25
CAPTURE PHASE | C2 | Opportunity Pipeline | Resource Forecasting | Estimate bid resource requirement (days by role) based on opportunity size/complexity | Bid Manager | Bid Director | Technical Owner / SME | Resource Pool | Opportunity scoping note, historic bid benchmarks | Bid resource plan, indicative cost-to-bid estimate | Resource Commitment Approval | Medium | Sequential
CAPTURE PHASE | C3 | Solution Development | Early Solution Shaping | Facilitate solution ideation workshop with Technical/Solution Owner | Solution Architect | Technical/Solution Owner | SME Panel | Bid Director | Client requirements brief, buyer values, prior art library | Draft solution concept, key assumptions log |  | High | Sequential
CAPTURE PHASE | C3 | Solution Development | Early Solution Shaping | Map proposed solution against client's functional and technical requirements | Technical/Solution Owner | Solution Architect | Delivery Director | Bid Manager | Client requirements document, solution concept | Requirements traceability matrix (RTM) v0.1 |  | High | Sequential | PFC Slide 10
CAPTURE PHASE | C3 | Solution Development | Partnership & Supply Chain Assessment | Identify and assess potential subcontractors, partners and advisors | Commercial Lead | Bid Director | Procurement Lead | Partner Management | Solution concept, SME requirements map | Partner long-list, NDA/teaming agreement log |  | Medium | Parallel | PFC Slide 16
CAPTURE PHASE | C3 | Solution Development | Partnership & Supply Chain Assessment | Evaluate partner capability, security clearance and compliance status | Commercial Lead | Bid Director | Legal | Partner | Partner submissions, DD questionnaires | Partner shortlist, teaming agreement v1 | Partner Sign-off Gate | Medium | Sequential
CAPTURE PHASE | C4 | Value Proposition Development | Value Proposition Design | Develop customer-centric value proposition aligned to buyer values | Capture Lead | Bid Director | Solution Architect / Commercial Lead | Account Manager | Buyer values register, solution concept | Value proposition statement, benefits realisation map |  | High | Iterative | Shipley Ghost Writing; PFC Slide 25
CAPTURE PHASE | C4 | Value Proposition Development | Value Proposition Design | Develop elevator pitch (outside-in) and value statement (inside-out) | Bid / Pursuit Lead | Bid Director | Commercial Lead | Bid Manager | Value proposition, win themes | Elevator pitch draft, value statement draft |  | Medium | Sequential | PFC Slide 25
CAPTURE PHASE | C4 | Value Proposition Development | Competitive Analysis | Map competitive landscape into Incumbents / Contenders / Dark Horse / Opportunists | Capture Lead | Bid Director | Market Intelligence | Partner | Market intel, procurement history | Competitive landscape map |  | Medium | Sequential | PFC Slide 15
CAPTURE PHASE | C4 | Value Proposition Development | Competitive Analysis | Develop counter-strategies for each credible competitor | Bid / Pursuit Lead | Bid Director | Solution Architect | Commercial Lead | Competitive map, win themes | Counter-strategy register | Win Strategy Gate (Bid Board) | High | Sequential
CAPTURE PHASE | C5 | Bid Mandate / Approval | Bid Mandate Preparation | Prepare formal Bid Mandate for Bid Board approval (budget, resource, win themes, risk) | Bid Manager | Bid Director | Commercial Lead / Legal | Partner | DQC, PWIN score, resource plan, solution concept | Bid Mandate document | BID BOARD FORMAL MANDATE APPROVAL | High | Sequential | Corporate governance
PROPOSAL PHASE | P1 | Kick-off | Bid Kick-off Workshop | Confirm bid team structure, assign roles and RACI across all workstreams | Bid Manager | Bid Director | All Workstream Leads | Bid Board | Bid Mandate, resource plan, win strategy | RACI matrix, bid team register, comms plan |  | Medium | Sequential
PROPOSAL PHASE | P1 | Kick-off | Bid Kick-off Workshop | Agree master bid programme with milestones, reviews, and submission date | Bid Manager | Bid Director | Workstream Leads | Commercial Lead | ITT/ITN timeline, resource plan | Master bid programme (Gantt), milestone tracker | Programme Baseline Gate | Medium | Sequential
PROPOSAL PHASE | P1 | Kick-off | Bid Management Plan (BMP) | Produce Bid Management Plan covering scope, governance, quality, and risk | Bid Manager | Bid Director | All Leads | Partner / Legal | Bid Mandate, kick-off outputs | Bid Management Plan v1 | BMP Sign-off by Bid Director | High | Sequential
PROPOSAL PHASE | P1 | Kick-off | Bid Management Plan (BMP) | Establish document management, version control and collaboration platform | Bid Manager | Bid Director | IT / Bid Support | All Team | Approved tooling/platform (SharePoint, Teams etc.) | Bid repository structure, naming convention guide |  | Low | Sequential
PROPOSAL PHASE | P1 | Kick-off | Compliance Checking | Perform detailed compliance check against all ITT/ITN requirements | Bid Manager | Bid Director | Legal / Commercial | Solution Owner | ITT/ITN documentation, compliance checklist template | Compliance matrix, mandatory requirements register |  | High | Sequential | PFC Slide 11
PROPOSAL PHASE | P2 | Commercial Strategy | Commercial Model Development | Develop commercial model and pricing strategy (budget modelling by workstream) | Commercial Lead | Bid Director | Finance / SME Leads | Partner | Solution concept, partner costs, benchmark data | Commercial model v1, pricing assumptions register |  | High | Sequential
PROPOSAL PHASE | P2 | Commercial Strategy | Commercial Model Development | Stress test pricing against win price intelligence and competitive benchmarks | Commercial Lead | Bid Director | Capture Lead | Finance | Commercial model, competitive landscape data | Sensitivity analysis, win price range |  | High | Iterative | PFC Slide 27
PROPOSAL PHASE | P2 | Commercial Strategy | T&C Negotiation Planning | Review client T&Cs, identify risk areas, prepare redline and negotiation strategy | Commercial Lead | Bid Director | Legal | Senior Responsible Exec | Client draft T&Cs, corporate risk policy | T&C risk register, redline document, negotiation plan | Commercial Risk Gate (Bid Board) | High | Sequential
PROPOSAL PHASE | P2 | Commercial Strategy | Pricing Sign-off | Present commercial model to Bid Board for formal pricing approval | Commercial Lead | Bid Director / Partner | Finance / Legal | All Leads | Commercial model, risk register, sensitivity analysis | Board-approved pricing mandate | FORMAL PRICING APPROVAL GATE | High | Sequential
PROPOSAL PHASE | P3 | Solution Design | Solution Architecture & Design | Develop full solution architecture responding to each requirement in RTM | Technical/Solution Owner | Bid Director | SME Panel | Delivery Director | RTM v0.1, client requirements, partner inputs | Solution design document, updated RTM v1 |  | High | Iterative
PROPOSAL PHASE | P3 | Solution Design | Solution Architecture & Design | Create solution storyboards per evaluation section | Technical/Solution Owner | Solution Architect | Bid Writers | Bid Manager | Win themes, solution design, evaluation criteria | Section storyboards (one per evaluation lot/question) | Storyboard Sign-off Gate | High | Sequential | Shipley Storyboarding
PROPOSAL PHASE | P3 | Solution Design | Transition & Transformation Planning | Develop transition/mobilisation plan including TUPE, asset transfer and phasing | Delivery/Transformation Director | Technical Owner | HR / Legal | Commercial Lead | Contract scope, workforce data, client incumbent info | Transition plan v1, TUPE schedule, risk log |  | High | Sequential
PROPOSAL PHASE | P3 | Solution Design | Risk & Assurance Planning | Identify, assess and mitigate delivery risks for solution | Delivery Director | Bid Director | SME / Commercial | Risk Manager | Solution design, transition plan | Risk register, risk mitigation plan |  | Medium | Iterative
PROPOSAL PHASE | P4 | Proposal Writing | Content Planning | Allocate writing responsibilities per section; develop section outlines against evaluation criteria | Bid Manager | Bid Director | All Workstream Leads | Bid Writers | ITT/ITN, evaluation criteria, storyboards | Section ownership matrix, section outlines |  | Medium | Sequential
PROPOSAL PHASE | P4 | Proposal Writing | Content Planning | Brief each writer using storyboard and win themes; confirm word counts and formats | Bid Manager | Bid Director | Technical Owner / Commercial | Writers | Storyboards, ITT instructions | Writer briefs (one per section), response format guide |  | Low | Sequential
PROPOSAL PHASE | P4 | Proposal Writing | Draft Writing | Produce Section 1 drafts (Executive Summary, Win Narrative, Key Themes) | Senior Bid Writer | Bid / Pursuit Lead | Capture Lead / Commercial | Bid Manager | Writer briefs, storyboards, win themes | Executive summary draft, section drafts v0.1 |  | High | Parallel | Shipley 20% Rule
PROPOSAL PHASE | P4 | Proposal Writing | Draft Writing | Produce technical and solution section drafts across all lots/questions | Technical Bid Writer / SME | Technical Owner | Solution Architect | Bid Manager | RTM, solution design, writer briefs | Technical section drafts v0.1 |  | High | Parallel
PROPOSAL PHASE | P4 | Proposal Writing | Draft Writing | Produce commercial and pricing schedules | Commercial Lead | Bid Director | Finance | Legal | Approved pricing mandate, T&C redline | Pricing schedules, commercial response drafts |  | High | Sequential
PROPOSAL PHASE | P5 | Content Library | Content Library Management | Retrieve and adapt approved boilerplate and evidence from content library | Bid Coordinator | Bid Manager | Subject Matter Experts | Writers | Content library / knowledge base | Adapted reuse content, flagged gaps |  | Low | Parallel
PROPOSAL PHASE | P5 | Content Library | Content Library Management | Commission new case studies and evidence where library gaps identified | Bid Coordinator | Bid Manager | SMEs / Account Managers | Partner | Gap analysis, approved evidence requests | New case studies, reference letters, CVs |  | Medium | Parallel
PROPOSAL PHASE | P6 | Proposal Review | Pink Team Review (30-50% draft) | Conduct Pink Team review against evaluation criteria; assess win theme penetration | Independent Reviewer | Bid Director | Capture Lead / Commercial | All Writers | Section drafts v0.1, evaluation criteria, win themes | Pink Team review report, action log | PINK TEAM GATE – proceed/rework decision | High | Sequential | Shipley Colour Reviews
PROPOSAL PHASE | P6 | Proposal Review | Red Team Review (80-90% draft) | Conduct Red Team review — evaluator simulation against scoring criteria | Senior Independent Panel | Bid Director | Solution Owner / Commercial | Bid Manager | Near-final drafts, evaluation model | Red Team scores, gap analysis, priority actions | RED TEAM GATE — approve for final production | High | Sequential | Shipley Colour Reviews
PROPOSAL PHASE | P6 | Proposal Review | Gold Team Review (Final) | Final executive quality review; confirm compliance, completeness and tone | Bid Board (Partner level) | Senior Responsible Exec | Commercial / Legal | Bid Manager | Final draft proposal | Gold Team sign-off, approved final document | GOLD SIGN-OFF GATE — authorise submission | High | Sequential
PROPOSAL PHASE | P7 | Production & Delivery | Document Production & Formatting | Apply corporate template, branding, page limits and formatting requirements | Bid Coordinator / DTP | Bid Manager | Brand/Design | Bid Director | Approved final content, ITT formatting requirements | Formatted proposal document(s) |  | Medium | Sequential
PROPOSAL PHASE | P7 | Production & Delivery | Document Production & Formatting | Proof-read, spell-check, and cross-reference all sections | Bid Coordinator | Bid Manager | Senior Bid Writer |  | Formatted document | Proof-read final document, error log cleared |  | Medium | Sequential
PROPOSAL PHASE | P7 | Production & Delivery | Final Compliance Check & Submission | Conduct final compliance check against all mandatory requirements before submission | Bid Manager | Bid Director | Legal / Commercial |  | Compliance matrix, final formatted document | Compliance sign-off sheet | FINAL COMPLIANCE GATE | High | Sequential
BID & PURSUIT PHASE | B1 | RFI Submission | RFI Response Management | Review RFI requirements and produce response plan | Bid Manager | Bid Director | Technical Owner | Commercial Lead | RFI document | RFI response plan, section ownership matrix |  | Low | Sequential
BID & PURSUIT PHASE | B1 | RFI Submission | RFI Response Management | Draft and review RFI response, confirm capability and interest | Bid Writer / SME | Bid Manager | Technical Owner / Commercial | Bid Director | RFI response plan, capability evidence | Completed RFI response | RFI Sign-off Gate | Medium | Sequential
BID & PURSUIT PHASE | B2 | Pre-Proposal Planning | Procurement Process Mapping | Map procurement timeline, evaluation stages, and decision milestones | Bid Manager | Bid Director | Commercial Lead | Capture Lead | OJEU/ITT notice, procurement documents | Procurement process map, master bid timeline |  | Medium | Sequential | PFC Slide 12
BID & PURSUIT PHASE | B2 | Pre-Proposal Planning | Clarification Question Strategy | Develop list of strategic clarification questions to shape the solution and reduce ambiguity | Technical Owner / Commercial | Bid Director | SME Panel | Bid Manager | ITT/ITN, RTM, risk register | Clarification Q list, prioritised by impact |  | Medium | Sequential
BID & PURSUIT PHASE | B2 | Pre-Proposal Planning | Clarification Question Strategy | Submit clarification questions within procurement deadlines and track responses | Bid Manager | Bid Director | All Workstream Leads |  | Approved Q list, procurement portal access | Submitted Qs, clarification response log |  | Low | Sequential
BID & PURSUIT PHASE | B3 | Bid Resource Allocation | Resource Mobilisation | Confirm and mobilise full bid team (internal + partner + contingency) | Bid Manager | Bid Director | HR / Resource Pool | Partner | Bid Mandate, resource plan | Confirmed team roster, onboarding pack | Resource Mobilisation Gate | Medium | Sequential
BID & PURSUIT PHASE | B3 | Bid Resource Allocation | Resource Mobilisation | Establish security clearance requirements and initiate vetting if required | HR / Security Manager | Bid Director | Legal | Team Members | Contract security schedule, team list | Vetting status tracker, cleared personnel log |  | Medium | Parallel | Defence/Justice context
BID & PURSUIT PHASE | B4 | Qualification | Win Strategy Refresh | Refresh and validate win strategy, PWIN score and competitive intelligence post-ITT receipt | Bid / Pursuit Lead | Bid Director | Capture Lead / Commercial | Bid Board | ITT/ITN, win strategy, PWIN score | Updated win strategy, refreshed PWIN score | Bid Board Win Strategy Re-confirmation | High | Sequential
BID & PURSUIT PHASE | B4 | Qualification | Win Strategy Refresh | Update stakeholder map and adjust client engagement plan post-ITT | Capture Lead / Account Manager | Bid Director | Bid Manager |  | Stakeholder map, ITT requirements | Updated stakeholder plan, revised engagement actions |  | Medium | Sequential
BID & PURSUIT PHASE | B5 | RFP / ITT Submission | Final Submission Management | Execute submission plan: upload, portal submission, confirmation receipt | Bid Manager | Bid Director | IT Support | Commercial Lead | Gold-approved documents, submission portal credentials | Submission confirmation, submitted documents archive | SUBMISSION CONFIRMATION GATE | High | Sequential
BID & PURSUIT PHASE | B5 | RFP / ITT Submission | Submission Debrief (Internal) | Conduct internal hot debrief within 48 hours of submission | Bid Manager | Bid Director | All Leads |  | Submission record, team feedback | Hot debrief notes, lessons log v1 |  | Low | Sequential
BID & PURSUIT PHASE | B6 | Bid Presentation | Presentation Preparation | Design and develop bid presentation (slides, narrative, evidence, demos) | Bid / Pursuit Lead | Bid Director | Solution Owner / Commercial | Bid Manager | Submitted proposal, evaluation feedback (if available), win themes | Presentation deck, speaker notes, rehearsal plan |  | High | Sequential
BID & PURSUIT PHASE | B6 | Bid Presentation | Presentation Preparation | Conduct structured presentation rehearsals and coaching (Boardroom Simulator) | Bid / Pursuit Lead | Senior Responsible Exec | SME / Commercial | Bid Manager | Presentation deck, evaluator model, coaching plan | Rehearsal debrief notes, revised deck | Rehearsal Sign-off Gate (Pursuit Lead) | High | Iterative | Boardroom Simulator tool
BID & PURSUIT PHASE | B6 | Bid Presentation | Presentation Delivery | Deliver bid presentation to evaluation panel; manage Q&A | Bid Director / Senior Exec | Senior Responsible Exec | Commercial / Technical | Bid Manager | Approved presentation, rehearsal outcomes | Presentation delivered, Q&A record | CLIENT EVALUATION — FORMAL SCORING | High | Sequential
BID & PURSUIT PHASE | B7 | Clarifications | Post-Submission Clarification Management | Receive, log and triage all post-submission clarification requests from client | Bid Manager | Bid Director | All Workstream Leads | Commercial Lead | Client clarification requests | Clarification log, triage register |  | Medium | Iterative
BID & PURSUIT PHASE | B7 | Clarifications | Post-Submission Clarification Management | Draft, review and submit clarification responses within deadlines | Technical Owner / Commercial | Bid Director | Legal / SME | Bid Manager | Clarification log, approved response process | Submitted clarification responses, updated risk log |  | High | Iterative
BID & PURSUIT PHASE | B8 | Bid Negotiations | Commercial & Contract Negotiation | Lead commercial and T&C negotiations with client procurement team | Commercial Lead | Bid Director | Legal / Senior Exec | Finance | Preferred bidder notification, client T&Cs, commercial model | Negotiated T&C schedule, agreed pricing |  | High | Iterative
BID & PURSUIT PHASE | B8 | Bid Negotiations | Commercial & Contract Negotiation | Obtain internal approval for any material changes to commercial position | Commercial Lead | Partner / Senior Responsible Exec | Legal / Finance | Bid Director | Negotiation notes, proposed changes | Board-approved commercial mandate update | COMMERCIAL ESCALATION GATE | High | Sequential
BID & PURSUIT PHASE | B9 | Award | Award & Mobilisation Preparation | Receive and process contract award; initiate formal mobilisation workstream | Bid Manager / Programme Director | Senior Responsible Exec | Commercial / Legal | All Leads | Award letter, signed contract | Mobilisation plan v1, project initiation document | CONTRACT AWARD — TRANSITION TO DELIVERY | High | Sequential
BID & PURSUIT PHASE | B9 | Award | Award & Mobilisation Preparation | Conduct post-award knowledge transfer to delivery team | Bid Manager | Bid Director | Delivery Director | Programme Manager | Bid file, commercial model, risk register, RTM | Handover pack, delivery team briefed | Handover Sign-off Gate | High | Sequential
BID & PURSUIT PHASE | B10 | Learning Reviews | Win / Loss Debrief | Request and attend formal client debrief; capture scoring and feedback | Bid / Pursuit Lead | Bid Director | Commercial Lead | Bid Manager | Client debrief invitation, submitted proposal | Debrief notes, evaluator score card |  | Medium | Sequential
BID & PURSUIT PHASE | B10 | Learning Reviews | Win / Loss Debrief | Conduct internal lessons learned review with full bid team | Bid Manager | Bid Director | All Leads |  | Debrief notes, bid programme, team feedback | Lessons learned report, improvement actions |  | Medium | Sequential
BID & PURSUIT PHASE | B10 | Learning Reviews | Knowledge Capture & Library Update | Update content library with new case studies, evidence and reusable content | Bid Coordinator | Bid Manager | SMEs | All | Lessons learned report, approved new content | Updated content library entries |  | Low | Sequential
BID & PURSUIT PHASE | B11 | Contract Renewal Strategy | Re-bid Planning | Initiate re-bid / contract renewal strategy 18-24 months before expiry | Capture Lead | Bid Director | Account Manager | Commercial Lead | Contract expiry schedule, client relationship data | Re-bid strategy plan, early engagement plan | RE-BID DECISION GATE (Bid Board) | High | Sequential | Cycle restart → C1

## RACI Matrix
BIP BID LIFECYCLE — RACI SUMMARY MATRIX (R=Responsible A=Accountable C=Consulted I=Informed)
Phase | L1 Stage | SRIE/Bid Sponsor | Bid Director | Bid/Pursuit Lead | Bid Manager | Commercial Lead | Solution/Technical Owner | Delivery Director | SME | Legal | Bid Writer/Coordinator | Partner
CAPTURE | C1 Customer Req Identified | I | A | R | C | C | C | I | C | I | I | I
CAPTURE | C2 Opportunity Pipeline | A | A | R | C | C | C | I | C | I | I | I
CAPTURE | C3 Solution Development | I | A | C | C | C | R | C | R | C | I | C
CAPTURE | C4 Value Proposition Dev | I | A | R | C | C | C | I | C | I | I | I
CAPTURE | C5 Bid Mandate / Approval | A | R | C | R | C | C | C | I | C | I | C
PROPOSAL | P1 Kick-off | I | A | C | R | C | C | C | I | I | C | I
PROPOSAL | P2 Commercial Strategy | I | A | C | C | R | C | C | C | R | I | C
PROPOSAL | P3 Solution Design | I | A | I | C | C | R | R | R | I | C | C
PROPOSAL | P4 Proposal Writing | I | A | C | R | C | C | C | C | C | R | I
PROPOSAL | P5 Content Library | I | I | I | A | I | C | I | C | I | R | I
PROPOSAL | P6 Proposal Review | A | R | C | R | C | C | C | C | I | C | I
PROPOSAL | P7 Production & Delivery | I | A | I | R | C | I | I | I | C | R | I
BID & PURSUIT | B1 RFI Submission | I | A | C | R | C | C | I | C | I | R | I
BID & PURSUIT | B2 Pre-Proposal Planning | I | A | C | R | C | C | I | C | I | I | I
BID & PURSUIT | B3 Bid Resource Alloc | I | A | C | R | I | I | I | I | I | I | I
BID & PURSUIT | B4 Qualification | A | R | R | C | C | I | I | I | I | I | I
BID & PURSUIT | B5 RFP/ITT Submission | I | A | C | R | C | C | I | I | C | R | I
BID & PURSUIT | B6 Bid Presentation | A | R | R | C | C | C | I | C | I | I | I
BID & PURSUIT | B7 Clarifications | I | A | I | R | C | R | I | C | C | I | I
BID & PURSUIT | B8 Bid Negotiations | A | R | I | C | R | I | I | I | R | I | C
BID & PURSUIT | B9 Award | A | R | C | C | C | I | R | I | C | I | I
BID & PURSUIT | B10 Learning Reviews | I | A | R | R | C | C | C | C | I | C | I
BID & PURSUIT | B11 Contract Renewal | I | A | R | C | C | I | I | I | I | I | C
R = Responsible
A = Accountable
C = Consulted
I = Informed

## Decision Gates Register
BIP BID LIFECYCLE — DECISION GATES & GOVERNANCE CHECKPOINTS
Gate Ref | Phase | Gate Name | Stage | Decision Authority | Pass Criteria (summary) | Output if PASS | Output if FAIL / Conditional
G1 | CAPTURE | Opportunity Screening Go/No-Go | C1 Customer Req Identified | Capture Lead + Bid Director | Meets minimum strategic fit, size and sector criteria | Add to opportunity pipeline | Reject / park for review
G2 | CAPTURE | Formal Bid Board Pursue Decision (DQC) | C2 Opportunity Pipeline | Bid Board (Partner level) | DQC score meets threshold; resource available; win probability ≥ target | Issue Bid Mandate; mobilise capture team | No-bid or conditional pursue with caveats
G3 | CAPTURE | Buyer Values Sign-off | C1 Customer Req Identified | Bid Director | Buyer values validated with ≥2 client stakeholders | Proceed to win strategy development | Return for further intelligence gathering
G4 | CAPTURE | Win Strategy Gate | C4 Value Proposition Dev | Bid Board | Win themes agreed; competitive strategy approved; PWIN updated | Proceed to Bid Mandate preparation | Rework strategy; request further intel
G5 | CAPTURE | Bid Board Formal Mandate Approval | C5 Bid Mandate | Partner / Senior Responsible Exec | Budget approved; resource confirmed; win strategy signed off | Issue formal Bid Mandate; mobilise bid team | Conditional approval / no-bid
G6 | PROPOSAL | Programme Baseline Gate | P1 Kick-off | Bid Director | Master bid programme baselined; RACI confirmed | Commence writing and solution design | Revise programme; resolve resource gaps
G7 | PROPOSAL | Storyboard Sign-off | P3 Solution Design | Bid Director + Technical Owner | All section storyboards approved; win themes embedded | Issue writer briefs; commence drafting | Rework storyboards
G8 | PROPOSAL | Commercial Risk Gate | P2 Commercial Strategy | Bid Board | Pricing strategy approved; T&C risk within tolerance | Proceed to detailed commercial drafting | Escalate risk; renegotiate partner terms
G9 | PROPOSAL | Pink Team Gate (30-50%) | P6 Proposal Review | Independent Review Panel | Pink Team score meets minimum threshold per section | Continue writing to Red Team | Major rework required; extend programme
G10 | PROPOSAL | Red Team Gate (80-90%) | P6 Proposal Review | Senior Independent Panel | Red Team scores above minimum; all critical gaps addressed | Proceed to Gold Team & production | Priority rework; possible extension request
G11 | PROPOSAL | Gold Sign-off Gate (Final) | P6 Proposal Review | Partner / Senior Responsible Exec | Full compliance confirmed; executive endorsement | Release for production and submission | Hold; fix critical issues
G12 | PROPOSAL | Final Compliance Gate | P7 Production & Delivery | Bid Manager + Bid Director | All mandatory requirements met; no compliance gaps | Submit | Do not submit; raise with client if deadline allows
G13 | BID & PURSUIT | Resource Mobilisation Gate | B3 Bid Resource Allocation | Bid Director | Full team confirmed; clearances initiated; partner signed | Commence proposal phase | Escalate resource gap to Partner
G14 | BID & PURSUIT | Win Strategy Re-confirmation | B4 Qualification | Bid Board | Win strategy valid post-ITT; PWIN reassessed; proceed justified | Confirm full bid commitment | Trigger no-bid / partial response
G15 | BID & PURSUIT | Submission Confirmation | B5 RFP/ITT Submission | Bid Manager | Submitted on portal; confirmation receipt obtained | Archive submission; commence pursuit activities | Escalate to client; explore late submission
G16 | BID & PURSUIT | Rehearsal Sign-off | B6 Bid Presentation | Bid/Pursuit Lead | Team ready; presentation rehearsed ≥3 times; Q&A prepared | Attend client presentation | Further rehearsal; coaching
G17 | BID & PURSUIT | Commercial Escalation Gate | B8 Bid Negotiations | Partner / Finance Director | Material changes within board-approved mandate | Sign revised commercial schedule | Escalate to Bid Board
G18 | BID & PURSUIT | Contract Award — Transition Gate | B9 Award | Senior Responsible Exec + Programme Director | Contract signed; mobilisation plan approved | Handover to delivery; close bid file | Standstill / debrief; explore challenge options
G19 | BID & PURSUIT | Re-bid Decision Gate | B11 Contract Renewal Strategy | Bid Board | Renewal strategy approved; early engagement plan active | Restart Capture Phase (C1) | Decide not to re-bid; exit strategy

## Roles & Responsibilities
BIP BID TEAM — ROLES & RESPONSIBILITIES REFERENCE
Role | Abbreviation | Primary Responsibilities (summary) | Key Activities in Bid Lifecycle | Typical Seniority / Function
Senior Responsible Industry Exec (SRIE) / Bid Sponsor | SRIE | Overall accountability for the bid. Provides leadership, vision, client engagement and authority to mobilise resources. | Bid Board chair. Approves key gates (Mandate, Gold sign-off, Award). Senior client relationship holder. | Partner / Managing Director
Bid Director | BD | Win strategy and client engagement lead. Bid quality assurance. Partner management. Chairs Bid Board. | Signs off win strategy, storyboards, commercial model. Leads Red/Gold review. Drives PWIN. | Director / Senior Manager
Bid / Pursuit Lead | BPL | Leads BD aspects: relationship development, win pitch strategy, client team coaching. Manages pursuit. | Leads qualification, pursuit strategy, win themes, presentation coaching, client interviews. | Director / Associate Director
Bid Manager | BM | Manages all bid production: documents, presentations, programme, stakeholder comms, compliance. | Produces BMP, master programme, chairs progress reviews, manages portal submissions, debrief. | Manager / Senior Consultant
Technical / Solution Owner | TSO | Design authority. Owns solution architecture and RTM. Ensures capability and standards compliance. | Solution workshops, storyboards, RTM, Green/Red reviews, clarification responses. | Technical Director / Principal Consultant
Delivery / Transformation Director | DTD | Programme design, transition plan, ICT/change authority. Monitors delivery risk. | Transition plan, TUPE, ICT architecture, risk mitigation in delivery sections. | Director / Programme Director
Commercial Lead | CL | Commercial model, pricing, T&C negotiation, budget modelling with workstream leads. | Commercial model, pricing approval, T&C redline, negotiation, partner cost management. | Commercial Director / Finance
Solution Architect | SA | Technical solution design, responds to requirements, develops RTM and service architecture. | Solution ideation workshops, RTM, storyboards, section drafting. | Senior Consultant / Architect
Subject Matter Expert (SME) | SME | Provides specialist knowledge in specific service/domain areas. Authors technical content. | Solution input, section drafting, Red Team, clarification support. | Consultant to Director level
Bid Writer / Senior Bid Writer | BW | Produces high-quality proposal content. Translates storyboards into compelling bid responses. | All proposal writing sections, Executive Summary, reuse content, proof reading. | Bid Writer / Senior Consultant
Bid Coordinator | BC | Document management, content library, formatting, production, portal submission support. | Repository management, DTP, proof-reading, submission logistics, content library updates. | Coordinator / Analyst
Legal | LEG | T&C review and redlining, contract risk, partner agreement sign-off. | T&C strategy, NDA/teaming, partner agreements, clarification legal review. | Legal Counsel / External
Partner / Sub-contractor | PART | Delivers specific solution components. Provides cost inputs and capability evidence. | Partner assessment, teaming agreement, solution input, cost submission. | External Partner

## Legend & Glossary
BIP BID LIFECYCLE WORKBOOK — LEGEND, COLOUR KEY & GLOSSARY
COLOUR KEY
Phase — Capture | Dark Blue header | Customer requirement identification through bid mandate approval
Phase — Proposal | Dark Green header | Kick-off through production and delivery of proposal documents
Phase — Bid & Pursuit | Dark Purple header | RFI through contract award and learning reviews
L1 Stage (header) | Mid-shade fill | Top-level process stage within a phase
L2 Sub-Process | Light-shade fill | Sub-process grouping within an L1 stage
L3 Task | Pale-shade fill | Individual activity / task within an L2 sub-process
Decision Gate | Gold / Amber | Formal governance checkpoint requiring an authorised decision
Effort — Low | Green | Up to 1 day equivalent resource effort
Effort — Medium | Amber | 1–5 days equivalent resource effort
Effort — High | Red | 5+ days / multi-resource effort; typically milestone activity
Type — Sequential | Light Blue | Activity must follow the previous step in order
Type — Parallel | Light Amber | Activity can run concurrently with other activities
Type — Iterative | Light Pink | Activity repeats/loops until quality criteria are met
RACI KEY
R — Responsible | Green | The role that does the work / produces the output
A — Accountable | Blue | The role that owns the outcome and signs off (only one per activity)
C — Consulted | Amber | Roles whose input is sought before the activity is completed
I — Informed | Grey | Roles kept informed of progress / outcomes
GLOSSARY
APMP | Association of Proposal Management Professionals | International bid management professional body
BMP | Bid Management Plan | Master governance document for the bid
DQC | Deal Qualification Checklist | Formal tool to decide pursue / no-pursue
DMU | Decision-Making Unit | All client stakeholders involved in evaluation and award decision
ITT/ITN | Invitation to Tender / Negotiate | Formal client procurement document
OJEU/FaT | Official Journal EU / Find a Tender | UK public procurement notice portals
PWIN | Probability of Win | Scored assessment of likelihood of winning the opportunity
RACI | Responsible/Accountable/Consulted/Informed | Governance role assignment model
RTM | Requirements Traceability Matrix | Maps each client requirement to a solution response
SRIE | Senior Responsible Industry Executive | Executive bid sponsor / senior accountable owner
Storyboard | Section narrative plan | Pre-writing plan aligning win themes to each evaluation question
TUPE | Transfer of Undertakings (Protection of Employment) Regs 2006 | UK legislation governing staff transfer on contract award