## L3 Task Review
Workstream | Activity Code | Activity Name | Mapping Status | Activity Output | L2 Sub-Process | Playbook Ref | L3 Task | R (Responsible) | A (Accountable) | C (Consulted) | I (Informed) | Inputs (pre-requisites) | Outputs (deliverables) | Effort | Type | YOUR REVIEW: Accept? (Y/N/Modify) | YOUR REVIEW: Comments / Changes
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Intelligence Gathering & Market Scanning | Playbook C1 | Monitor OJEU/Find-a-Tender for relevant procurement notices | Capture Lead | Bid Director | Market Intel Team | Bid Board | Market scan tools, sector intel reports, client relationship data | Long-list of target opportunities, opportunity log entry | Low | Sequential
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Intelligence Gathering & Market Scanning | Playbook C1 | Conduct stakeholder listening exercises with client contacts | Capture Lead | Bid Director | Account Manager | Commercial Lead | Existing relationship map, client org chart | Intelligence notes, relationship map update | Low | Parallel
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Intelligence Gathering & Market Scanning | Playbook C1 | Review customer strategic plans, spending reviews & published strategies | Market Intel Analyst | Capture Lead | SME | Bid Director | Published government/client strategy documents | Customer insight summary, hot spots register | Low | Sequential
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Customer Needs Analysis | Playbook C1 | Identify and map key stakeholders within the buying authority (DMU) | Capture Lead | Bid Director | Account Manager | Bid Manager | Org chart, previous bid history, relationship CRM data | Stakeholder/power map, DMU register | Medium | Sequential
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Customer Needs Analysis | Playbook C1 | Conduct structured interviews with key decision makers | Account Manager | Bid Director | Capture Lead | Commercial Lead | Stakeholder map, approved engagement plan | Interview notes, buyer values assessment | Medium | Iterative
SAL | SAL-01 | Customer engagement & intelligence gathering | MAPPED | Customer intelligence briefing | Customer Needs Analysis | Playbook C1 | Document and validate buyer values and evaluation criteria | Capture Lead | Bid Director | Solution Architect | Commercial Lead | Interview outputs, ITN/OJEU notice | Buyer values register, weightings matrix | Medium | Sequential
SAL | SAL-01 | [5 empty] | REVIEW NOTE: Gate reference: Playbook has "Opportunity Screening Go/No-Go Gate" at C1 and "Buyer Values Sign-off Gate" at end of Customer Needs Analysis. Product doesn't have a buyer values gate — should it?
SAL | SAL-02 | Incumbent performance review (rebid) | PRODUCT ONLY | Incumbent performance assessment | Incumbent Performance Analysis | No playbook equivalent | Review incumbent's published performance data and KPIs | Capture Lead | Bid Director | Account Manager | Commercial Lead | Contract performance reports, FOI responses, client publications | Incumbent performance summary | Medium | Sequential
SAL | SAL-02 | Incumbent performance review (rebid) | PRODUCT ONLY | Incumbent performance assessment | Incumbent Performance Analysis | No playbook equivalent | Identify incumbent weaknesses and service gaps | Capture Lead | Bid Director | SME / Delivery Director | Solution Architect | Performance summary, client intelligence | Incumbent weakness register, ghost themes | Medium | Sequential
SAL | SAL-02 | Incumbent performance review (rebid) | PRODUCT ONLY | Incumbent performance assessment | Incumbent Performance Analysis | No playbook equivalent | Assess re-bid risk factors (TUPE, asset transfer, client loyalty) | Capture Lead | Bid Director | Commercial / Legal | Bid Manager | Contract terms, workforce data, client relationship assessment | Re-bid risk assessment | Medium | Parallel
SAL | SAL-02 | [5 empty] | REVIEW NOTE: This activity exists in the product but not the playbook. It applies to all opportunities (understanding the incumbent) but has additional depth for rebids. Per point 4 discussion: the "(rebid)" qualifier should be toggled on/off at bid setup based on incumbency. L3 tasks above are suggested — please review.
SAL | SAL-03 | Competitor analysis & positioning | MAPPED | Competitive landscape assessment | Competitive Analysis | Playbook C4 | Map competitive landscape into Incumbents / Contenders / Dark Horse / Opportunists | Capture Lead | Bid Director | Market Intelligence | Partner | Market intel, procurement history | Competitive landscape map | Medium | Sequential
SAL | SAL-03 | Competitor analysis & positioning | MAPPED | Competitive landscape assessment | Competitive Analysis | Playbook C4 | Develop counter-strategies for each credible competitor | Bid / Pursuit Lead | Bid Director | Solution Architect | Commercial Lead | Competitive map, win themes | Counter-strategy register | High | Sequential
SAL | SAL-03 | [5 empty] | REVIEW NOTE: Playbook has "Win Strategy Gate (Bid Board)" after counter-strategies. This maps to part of SAL-06 (win strategy lock) in the product.
SAL | SAL-04 | Win theme development & refinement | MAPPED | Win theme document | Win Probability & Theme Development | Playbook C2 | Identify win themes and preliminary differentiators vs likely competitors | Capture Lead | Bid Director | Solution Architect | Commercial Lead | Competitive landscape map, buyer values | Draft win themes register (3–5 themes) | Medium | Sequential
SAL | SAL-04 | Win theme development & refinement | MAPPED | Win theme document | Value Proposition Design | Playbook C4 | Develop customer-centric value proposition aligned to buyer values | Capture Lead | Bid Director | Solution Architect / Commercial Lead | Account Manager | Buyer values register, solution concept | Value proposition statement, benefits realisation map | High | Iterative
SAL | SAL-04 | Win theme development & refinement | MAPPED | Win theme document | Value Proposition Design | Playbook C4 | Develop elevator pitch (outside-in) and value statement (inside-out) | Bid / Pursuit Lead | Bid Director | Commercial Lead | Bid Manager | Value proposition, win themes | Elevator pitch draft, value statement draft | Medium | Sequential
SAL | SAL-05 | Evaluation criteria mapping & scoring strategy | PARTIAL | Evaluation criteria matrix with scoring approach | Evaluation Criteria Mapping | Derived from Playbook C1 (buyer values) + product extension | Document and validate buyer values and evaluation criteria | Capture Lead | Bid Director | Solution Architect | Commercial Lead | Interview outputs, ITN/OJEU notice | Buyer values register, weightings matrix | Medium | Sequential
SAL | SAL-05 | Evaluation criteria mapping & scoring strategy | PARTIAL | Evaluation criteria matrix with scoring approach | Evaluation Criteria Mapping | Derived from Playbook C1 (buyer values) + product extension | Map ITT evaluation criteria to response sections and scoring model | Bid Manager | Bid Director | Capture Lead | Solution Architect | ITT evaluation model, buyer values register | Evaluation criteria matrix | Medium | Sequential
SAL | SAL-05 | Evaluation criteria mapping & scoring strategy | PARTIAL | Evaluation criteria matrix with scoring approach | Evaluation Criteria Mapping | Derived from Playbook C1 (buyer values) + product extension | Develop scoring optimisation strategy per evaluation section | Bid Manager | Bid Director | Capture Lead / Commercial | Writers | Evaluation criteria matrix, competitive positioning | Scoring strategy document | Medium | Sequential
SAL | SAL-05 | [5 empty] | REVIEW NOTE: Playbook covers buyer values validation (C1) but not the deeper scoring strategy work. Last two tasks are suggested additions to fill the gap. Review whether this level of detail is right.
SAL | SAL-06 | Capture plan finalisation & win strategy lock | MAPPED | Capture plan (locked) — METHODOLOGY GATE | Opportunity Qualification | Playbook C2 | Complete Deal Qualification Checklist (DQC) covering attractiveness, deliverability, risk & win likelihood | Bid Director | Senior Responsible Exec | Commercial Lead / SME | Bid Board | Opportunity brief, buyer values, market intel, resource forecast | DQC completed artefact, pursue/no pursue recommendation | High | Sequential
SAL | SAL-06 | Capture plan finalisation & win strategy lock | MAPPED | Capture plan (locked) — METHODOLOGY GATE | Opportunity Qualification | Playbook C2 | Assess strategic fit against sector portfolio and growth plan | Bid Director | Partner | Capture Lead | Account Manager | Strategic plan, sector pipeline data | Strategic fit assessment, risk-adjusted pipeline entry | Medium | Sequential
SAL | SAL-06 | Capture plan finalisation & win strategy lock | MAPPED | Capture plan (locked) — METHODOLOGY GATE | PWIN Assessment | Playbook C2 | Score opportunity against competitive position, relationships and solution readiness | Bid Director | Partner | Capture Lead / Commercial Lead | Bid Manager | DQC output, competitive intelligence, stakeholder map | PWIN score (%), PWIN rationale note | Medium | Iterative
SAL | SAL-06 | Capture plan finalisation & win strategy lock | MAPPED | Capture plan (locked) — METHODOLOGY GATE | Bid Mandate Preparation | Playbook C5 | Prepare formal Bid Mandate for Bid Board approval (budget, resource, win themes, risk) | Bid Manager | Bid Director | Commercial Lead / Legal | Partner | DQC, PWIN score, resource plan, solution concept | Bid Mandate document | High | Sequential
SAL | SAL-06 | [5 empty] | REVIEW NOTE: Playbook gate: "BID BOARD FORMAL MANDATE APPROVAL" at C5. This maps to product gate G1 (Pursuit Approval). SAL-06 is also a METHODOLOGY GATE in the product.
SAL | SAL-07 | Pre-submission clarification strategy & drafting | MAPPED | Clarification question register (prioritised) | Clarification Question Strategy | Playbook B2 | Develop list of strategic clarification questions to shape the solution and reduce ambiguity | Technical Owner / Commercial | Bid Director | SME Panel | Bid Manager | ITT/ITN, RTM, risk register | Clarification Q list, prioritised by impact | Medium | Sequential
SOL | SOL-01 | Requirements analysis & interpretation | MAPPED | Requirements interpretation document | Requirements Analysis | Playbook C3 + P3 | Map proposed solution against client's functional and technical requirements | Technical/Solution Owner | Solution Architect | Delivery Director | Bid Manager | Client requirements document, solution concept | Requirements traceability matrix (RTM) v0.1 | High | Sequential
SOL | SOL-01 | [5 empty] | REVIEW NOTE: Product activity is broader than the single playbook task. Additional L3 tasks likely needed: ITT document analysis, requirement categorisation, ambiguity identification, compliance gap analysis.
SOL | SOL-02 | Current service model review (rebid) | PRODUCT ONLY | As-is service model assessment | Current Service Model Assessment | No playbook equivalent | Document current service delivery model and operating structure | Delivery Director | Solution Architect | Account Manager | Bid Director | Current contract, service reports, org charts | As-is service model document | Medium | Sequential
SOL | SOL-02 | Current service model review (rebid) | PRODUCT ONLY | As-is service model assessment | Current Service Model Assessment | No playbook equivalent | Identify service gaps, pain points and improvement opportunities | Solution Architect | Technical Owner | SME / Delivery | Commercial Lead | As-is model, client feedback, performance data | Gap analysis, improvement register | Medium | Sequential
SOL | SOL-02 | [5 empty] | REVIEW NOTE: Per point 4: "(rebid)" qualifier toggleable at bid setup based on incumbency. Activity applies to all bids (understanding the current service) but framing changes. Tasks above are suggested — please review.
SOL | SOL-03 | Target operating model design | MAPPED | Target operating model | Early Solution Shaping | Playbook C3 | Facilitate solution ideation workshop with Technical/Solution Owner | Solution Architect | Technical/Solution Owner | SME Panel | Bid Director | Client requirements brief, buyer values, prior art library | Draft solution concept, key assumptions log | High | Sequential
SOL | SOL-03 | Target operating model design | MAPPED | Target operating model | Solution Architecture & Design | Playbook P3 | Develop full solution architecture responding to each requirement in RTM | Technical/Solution Owner | Bid Director | SME Panel | Delivery Director | RTM v0.1, client requirements, partner inputs | Solution design document, updated RTM v1 | High | Iterative
SOL | SOL-03 | [5 empty] | REVIEW NOTE: SOL-03 is a 45-day activity — the longest in the product. Likely needs more L3 tasks to decompose: e.g. operating model canvas, governance structure, service line architecture, scalability model.
SOL | SOL-04 | Service delivery model design | PARTIAL | Service delivery model | Service Delivery Architecture | Playbook P3 (implicit in solution design) | Design service delivery structure per service line | Solution Architect | Technical Owner | Delivery Director | Commercial Lead | Target operating model, client requirements | Service delivery model document | High | Sequential
SOL | SOL-04 | Service delivery model design | PARTIAL | Service delivery model | Service Delivery Architecture | Playbook P3 (implicit in solution design) | Define capacity and scalability model | Solution Architect | Technical Owner | Delivery Director | Commercial Lead | Demand projections, service levels | Capacity model, scalability assessment | Medium | Iterative
SOL | SOL-04 | Service delivery model design | PARTIAL | Service delivery model | Service Delivery Architecture | Playbook P3 (implicit in solution design) | Map SLA/KPI commitments to delivery components | Delivery Director | Technical Owner | Commercial Lead | Bid Manager | KPI framework (DEL-03), delivery model | SLA commitment matrix | Medium | Sequential
SOL | SOL-05 | Technology & digital approach | PRODUCT ONLY | Technology solution design | Technology & Digital Solution | No explicit playbook equivalent (embedded in P3 solution architecture) | Design technology architecture and digital platform approach | Technical Owner | Solution Architect | SME / Partner | Delivery Director | Target operating model, client tech requirements | Technology solution design | High | Iterative
SOL | SOL-05 | Technology & digital approach | PRODUCT ONLY | Technology solution design | Technology & Digital Solution | No explicit playbook equivalent (embedded in P3 solution architecture) | Assess integration requirements and data migration approach | Technical Owner | Solution Architect | Client IT (if available) | Bid Manager | As-is tech landscape, target architecture | Integration requirements, migration approach | Medium | Sequential
SOL | SOL-06 | Staffing model & TUPE analysis | MAPPED | Staffing model with TUPE schedule | Transition & Transformation Planning | Playbook P3 | Develop transition/mobilisation plan including TUPE, asset transfer and phasing | Delivery/Transformation Director | Technical Owner | HR / Legal | Commercial Lead | Contract scope, workforce data, client incumbent info | Transition plan v1, TUPE schedule, risk log | High | Sequential
SOL | SOL-06 | [5 empty] | REVIEW NOTE: Product splits staffing/TUPE (SOL-06) from transition planning (SOL-07) — playbook combines them. The split is right for the product but L3 tasks need to be separated accordingly. Additional staffing-specific tasks likely needed.
SOL | SOL-07 | Transition & mobilisation approach | PARTIAL | Transition plan | Transition Planning | Playbook P3 (shared with SOL-06) | Design mobilisation programme with phasing and milestones | Delivery Director | Technical Owner | Bid Manager / Commercial | Partner | Service delivery model, staffing model, TUPE schedule | Mobilisation programme, phase plan | High | Sequential
SOL | SOL-07 | Transition & mobilisation approach | PARTIAL | Transition plan | Transition Planning | Playbook P3 (shared with SOL-06) | Identify transition risks and develop mitigation strategies | Delivery Director | Technical Owner | Legal / Commercial | Bid Director | Transition plan, risk register | Transition risk register, mitigation actions | Medium | Iterative
SOL | SOL-08 | Innovation & continuous improvement | PRODUCT ONLY | Innovation roadmap | Innovation Strategy | No playbook equivalent | (No L3 tasks defined - needs authoring)
SOL | SOL-09 | Social value proposition | PRODUCT ONLY | Social value plan | Social Value Design | No playbook equivalent | (No L3 tasks defined - needs authoring)
SOL | SOL-10 | Evidence strategy & case study identification | MAPPED | Evidence requirements matrix | Content Library Management | Playbook P5 | Retrieve and adapt approved boilerplate and evidence from content library | Bid Coordinator | Bid Manager | SMEs | Writers | Content library / knowledge base | Adapted reuse content, flagged gaps | Low | Parallel
SOL | SOL-10 | Evidence strategy & case study identification | MAPPED | Evidence requirements matrix | Content Library Management | Playbook P5 | Commission new case studies and evidence where library gaps identified | Bid Coordinator | Bid Manager | SMEs / Account Managers | Partner | Gap analysis, approved evidence requests | New case studies, reference letters, CVs | Medium | Parallel
SOL | SOL-11 | Solution design lock | PARTIAL | Solution design pack (locked & assured) | Solution Lock & Assurance | Playbook P3 storyboard sign-off (partial) | Create solution storyboards per evaluation section | Technical/Solution Owner | Solution Architect | Bid Writers | Bid Manager | Win themes, solution design, evaluation criteria | Section storyboards (one per evaluation lot/question) | High | Sequential
SOL | SOL-11 | Solution design lock | PARTIAL | Solution design pack (locked & assured) | Solution Lock & Assurance | Playbook P3 storyboard sign-off (partial) | Consolidate all solution workstream outputs into locked design pack | Solution Architect | Technical Owner | All SOL contributors | Bid Director | All SOL-03 through SOL-09 outputs | Solution design pack (locked) | Medium | Sequential
SOL | SOL-11 | Solution design lock | PARTIAL | Solution design pack (locked & assured) | Solution Lock & Assurance | Playbook P3 storyboard sign-off (partial) | Conduct internal solution assurance review before governance gate | Technical Owner | Bid Director | Delivery Director / Commercial | Bid Manager | Solution design pack, risk register | Solution assurance record, residual issues log | High | Sequential
SOL | SOL-11 | [5 empty] | REVIEW NOTE: Per point 5: Completing SOL-11 should fire a "Solution Design Complete" milestone in the key milestones view. Playbook gate: "Storyboard Sign-off Gate" at P3.
SOL | SOL-12 | Solution risk identification & analysis | NEW — PROPOSED | Solution risk register | Risk & Assurance Planning | Playbook P3 | Identify, assess and mitigate delivery risks for solution | Delivery Director | Bid Director | SME / Commercial | Risk Manager | Solution design, transition plan | Risk register, risk mitigation plan | Medium | Iterative
SOL | SOL-12 | [5 empty] | REVIEW NOTE: Per point 6: New activity requested. Playbook P3 has "Risk & Assurance Planning" as explicit L2. Feeds into BM-13 (bid risk register) and DEL-06 (mitigated risk register). Dependencies: SOL-03, SOL-04.
COM | COM-01 | Should-cost model development | MAPPED | Should-cost model | Commercial Model Development | Playbook P2 | Develop commercial model and pricing strategy (budget modelling by workstream) | Commercial Lead | Bid Director | Finance / SME Leads | Partner | Solution concept, partner costs, benchmark data | Commercial model v1, pricing assumptions register | High | Sequential
COM | COM-02 | Price-to-win analysis | MAPPED | Price-to-win assessment | Competitive Pricing Analysis | Playbook P2 | Stress test pricing against win price intelligence and competitive benchmarks | Commercial Lead | Bid Director | Capture Lead | Finance | Commercial model, competitive landscape data | Sensitivity analysis, win price range | High | Iterative
COM | COM-03 | Subcontractor & supply chain pricing | PARTIAL | Partner pricing schedule | Partner Pricing | Implied in playbook P2 / C3 but not explicit L3 | (No L3 tasks defined - needs authoring)
COM | COM-04 | Commercial model & payment mechanisms | MAPPED | Commercial model document | T&C Negotiation Planning | Playbook P2 | Review client T&Cs, identify risk areas, prepare redline and negotiation strategy | Commercial Lead | Bid Director | Legal | Senior Responsible Exec | Client draft T&Cs, corporate risk policy | T&C risk register, redline document, negotiation plan | High | Sequential
COM | COM-05 | Margin structure & sensitivity analysis | PARTIAL | Margin model with sensitivities | Margin & Sensitivity Modelling | Implied within P2 commercial model tasks | (No L3 tasks defined - needs authoring)
COM | COM-06 | Pricing model finalisation | MAPPED | Pricing model (locked & assured) | Pricing Sign-off | Playbook P2 | Present commercial model to Bid Board for formal pricing approval | Commercial Lead | Bid Director / Partner | Finance / Legal | All Leads | Commercial model, risk register, sensitivity analysis | Board-approved pricing mandate | High | Sequential
COM | COM-06 | [5 empty] | REVIEW NOTE: Playbook gate: "FORMAL PRICING APPROVAL GATE" at P2. Maps to product gate G3 (Commercial / Finance Review).
COM | COM-07 | Commercial risk identification & analysis | NEW — PROPOSED | Commercial risk register | Commercial Risk Assessment | Playbook P2 (Commercial Risk Gate) | Identify commercial and pricing risks across all cost elements | Commercial Lead | Bid Director | Finance / Legal | Delivery Director | Commercial model, T&C markup, partner terms | Commercial risk register | Medium | Iterative
COM | COM-07 | Commercial risk identification & analysis | NEW — PROPOSED | Commercial risk register | Commercial Risk Assessment | Playbook P2 (Commercial Risk Gate) | Develop risk mitigation strategies and quantify contingency requirements | Commercial Lead | Bid Director | Legal / Delivery | Partner | Risk register, sensitivity analysis | Mitigation plan, contingency budget | Medium | Sequential
COM | COM-07 | [5 empty] | REVIEW NOTE: Per point 6: New activity requested. Playbook has "Commercial Risk Gate" at P2 which implies this work happens. Feeds into BM-13 and DEL-06. Dependencies: COM-01, COM-04, LEG-02.
LEG | LEG-01 | Contract review & markup | MAPPED | Contract markup with positions log | T&C Review | Playbook P2 | Review client T&Cs, identify risk areas, prepare redline and negotiation strategy | Commercial Lead | Bid Director | Legal | Senior Responsible Exec | Client draft T&Cs, corporate risk policy | T&C risk register, redline document, negotiation plan | High | Sequential
LEG | LEG-01 | [5 empty] | REVIEW NOTE: Same playbook L3 as COM-04 — the work spans both workstreams. In practice, Legal leads the markup, Commercial leads the negotiation strategy. RACI should reflect Legal as R for this activity.
LEG | LEG-02 | Risk allocation analysis | MAPPED | Risk allocation matrix | Risk & Assurance Planning | Playbook P3 | Identify, assess and mitigate delivery risks for solution (legal/contractual risk lens) | Legal | Bid Director | Commercial / Delivery | Risk Manager | Contract terms, solution design, transition plan | Risk allocation matrix | Medium | Iterative
LEG | LEG-03 | Insurance & liability review | PRODUCT ONLY | Insurance requirements assessment | Insurance Analysis | No playbook equivalent | (No L3 tasks defined - needs authoring)
LEG | LEG-04 | TUPE obligations assessment | PARTIAL | TUPE compliance assessment | TUPE Analysis | Playbook P3 (embedded in transition planning) | (No L3 tasks defined - needs authoring)
LEG | LEG-05 | Data protection & security review | PRODUCT ONLY | DPIA / security assessment | Data Protection & Security | No playbook equivalent (playbook has clearance vetting in B3 only) | (No L3 tasks defined - needs authoring)
LEG | LEG-06 | Subcontractor terms review | PARTIAL | Subcontract terms summary | Partner Compliance | Playbook C3 (partner assessment) | Evaluate partner capability, security clearance and compliance status | Commercial Lead | Bid Director | Legal | Partner | Partner submissions, DD questionnaires | Partner shortlist, teaming agreement v1 | Medium | Sequential
DEL | DEL-01 | Delivery risk & assumptions register | MAPPED | Delivery risk & assumptions register (living document) | Risk & Assurance Planning | Playbook P3 | Identify, assess and mitigate delivery risks for solution | Delivery Director | Bid Director | SME / Commercial | Risk Manager | Solution design, transition plan | Risk register, risk mitigation plan | Medium | Iterative
DEL | DEL-02 | Mobilisation & implementation planning | MAPPED | Mobilisation plan | Transition & Transformation | Playbook P3 (shared with SOL-07) | (No L3 tasks defined - needs authoring)
DEL | DEL-03 | Performance framework & KPIs/SLAs | PRODUCT ONLY | KPI/SLA framework | Performance Framework | No playbook equivalent | (No L3 tasks defined - needs authoring)
DEL | DEL-04 | Resource & capacity plan | PARTIAL | Resource plan | Resource Forecasting | Playbook C2 | Estimate bid resource requirement (days by role) based on opportunity size/complexity | Bid Manager | Bid Director | Technical Owner / SME | Resource Pool | Opportunity scoping note, historic bid benchmarks | Bid resource plan, indicative cost-to-bid estimate | Medium | Sequential
DEL | DEL-04 | [5 empty] | REVIEW NOTE: Playbook C2 resource forecasting is about bid team resources. DEL-04 is about delivery resources (the service team post-award). Different scope — L3 tasks need authoring for the delivery resource perspective.
DEL | DEL-05 | Business continuity & exit planning | PRODUCT ONLY | BC/exit plan | Business Continuity | No playbook equivalent | (No L3 tasks defined - needs authoring)
DEL | DEL-06 | Risk mitigation & residual acceptance | PARTIAL | Mitigated risk register (assured) | Risk Mitigation | Playbook P3 (continuation of DEL-01) | (No L3 tasks defined - needs authoring)
SUP | SUP-01 | Partner identification & selection | MAPPED | Partner shortlist with rationale | Partnership & Supply Chain Assessment | Playbook C3 | Identify and assess potential subcontractors, partners and advisors | Commercial Lead | Bid Director | Procurement Lead | Partner Management | Solution concept, SME requirements map | Partner long-list, NDA/teaming agreement log | Medium | Parallel
SUP | SUP-01 | Partner identification & selection | MAPPED | Partner shortlist with rationale | Partnership & Supply Chain Assessment | Playbook C3 | Evaluate partner capability, security clearance and compliance status | Commercial Lead | Bid Director | Legal | Partner | Partner submissions, DD questionnaires | Partner shortlist, teaming agreement v1 | Medium | Sequential
SUP | SUP-02 | Partner solution inputs & design contribution | PRODUCT ONLY | Partner solution inputs pack | Partner Solution Integration | No explicit playbook L3 (product has right granularity) | (No L3 tasks defined - needs authoring)
SUP | SUP-03 | Teaming agreement negotiation | PARTIAL | Signed teaming agreements | Teaming Agreements | Implied in playbook C3 partner assessment | (No L3 tasks defined - needs authoring)
SUP | SUP-04 | Partner pricing | PRODUCT ONLY | Partner pricing schedules | Partner Commercial | No playbook L3 | (No L3 tasks defined - needs authoring)
SUP | SUP-05 | Partner credentials & references | PRODUCT ONLY | Partner case studies & CVs | Partner Evidence | No playbook L3 | (No L3 tasks defined - needs authoring)
SUP | SUP-06 | Back-to-back commercial terms | PRODUCT ONLY | Back-to-back terms agreed | Partner Contractual | No playbook L3 | (No L3 tasks defined - needs authoring)
BM | BM-01 | Kickoff planning & execution | MAPPED | Kickoff pack: strategy summary, RACI, timeline, comms plan | Bid Kick-off Workshop | Playbook P1 | Confirm bid team structure, assign roles and RACI across all workstreams | Bid Manager | Bid Director | All Workstream Leads | Bid Board | Bid Mandate, resource plan, win strategy | RACI matrix, bid team register, comms plan | Medium | Sequential
BM | BM-01 | Kickoff planning & execution | MAPPED | Kickoff pack: strategy summary, RACI, timeline, comms plan | Bid Kick-off Workshop | Playbook P1 | Agree master bid programme with milestones, reviews, and submission date | Bid Manager | Bid Director | Workstream Leads | Commercial Lead | ITT/ITN timeline, resource plan | Master bid programme (Gantt), milestone tracker | Medium | Sequential
BM | BM-01 | [5 empty] | REVIEW NOTE: Playbook gate: "Programme Baseline Gate" at P1. Not currently a product gate — should it be?
BM | BM-02 | Bid management plan production | MAPPED | Bid management plan (BMP) | Bid Management Plan | Playbook P1 | Produce Bid Management Plan covering scope, governance, quality, and risk | Bid Manager | Bid Director | All Leads | Partner / Legal | Bid Mandate, kick-off outputs | Bid Management Plan v1 | High | Sequential
BM | BM-03 | Document management & version control setup | MAPPED | Repository structure, naming conventions, platform | Document Management | Playbook P1 | Establish document management, version control and collaboration platform | Bid Manager | Bid Director | IT / Bid Support | All Team | Approved tooling/platform (SharePoint, Teams etc.) | Bid repository structure, naming convention guide | Low | Sequential
BM | BM-04 | Resource management & tracking | MAPPED | Resource tracker, security clearance log, availability register | Resource Mobilisation | Playbook B3 | Confirm and mobilise full bid team (internal + partner + contingency) | Bid Manager | Bid Director | HR / Resource Pool | Partner | Bid Mandate, resource plan | Confirmed team roster, onboarding pack | Medium | Sequential
BM | BM-04 | Resource management & tracking | MAPPED | Resource tracker, security clearance log, availability register | Resource Mobilisation | Playbook B3 | Establish security clearance requirements and initiate vetting if required | HR / Security Manager | Bid Director | Legal | Team Members | Contract security schedule, team list | Vetting status tracker, cleared personnel log | Medium | Parallel
BM | BM-04 | [5 empty] | REVIEW NOTE: Playbook gate: "Resource Mobilisation Gate" at B3. Product doesn't have this gate. Per your catch — resource mobilisation should be a formal checkpoint. Consider adding as a milestone.
BM | BM-05 | Bid cost management | PARTIAL | Cost-to-bid tracker | Cost-to-Bid Tracking | Partially in Playbook C2 resource forecasting | (No L3 tasks defined - needs authoring)
BM | BM-06 | Progress reporting | PRODUCT ONLY | Weekly progress reports, milestone achievement reports | Progress Reporting | No explicit playbook L3 (implied throughout) | (No L3 tasks defined - needs authoring)
BM | BM-07 | Quality management approach | PARTIAL | Quality plan: evaluation weighting analysis, page budgets | Compliance & Quality Planning | Playbook P1 | Perform detailed compliance check against all ITT/ITN requirements | Bid Manager | Bid Director | Legal / Commercial | Solution Owner | ITT/ITN documentation, compliance checklist template | Compliance matrix, mandatory requirements register | High | Sequential
BM | BM-08 | Stakeholder & communications management | PRODUCT ONLY | Stakeholder comms plan, decision log | Stakeholder Management | No explicit playbook L3 | (No L3 tasks defined - needs authoring)
BM | BM-09 | Competitive dialogue management (if applicable) | PRODUCT ONLY | Dialogue prep packs, session records, iteration tracker | Competitive Dialogue | No playbook equivalent (procurement route specific) | (No L3 tasks defined - needs authoring)
BM | BM-10 | Storyboard development & sign-off | MAPPED | Approved storyboard — METHODOLOGY GATE | Content Planning | Playbook P4 | Allocate writing responsibilities per section; develop section outlines against evaluation criteria | Bid Manager | Bid Director | All Workstream Leads | Bid Writers | ITT/ITN, evaluation criteria, storyboards | Section ownership matrix, section outlines | Medium | Sequential
BM | BM-10 | Storyboard development & sign-off | MAPPED | Approved storyboard — METHODOLOGY GATE | Content Planning | Playbook P4 | Brief each writer using storyboard and win themes; confirm word counts and formats | Bid Manager | Bid Director | Technical Owner / Commercial | Writers | Storyboards, ITT instructions | Writer briefs (one per section), response format guide | Low | Sequential
BM | BM-11 | Hot debrief (post-submission) | MAPPED | Hot debrief notes, immediate lessons log | Submission Debrief | Playbook B5 | Conduct internal hot debrief within 48 hours of submission | Bid Manager | Bid Director | All Leads | — | Submission record, team feedback | Hot debrief notes, lessons log v1 | Low | Sequential
BM | BM-12 | Lessons learned & knowledge capture | MAPPED | Lessons report, content library updates, process improvement actions | Win / Loss Debrief | Playbook B10 | Request and attend formal client debrief; capture scoring and feedback | Bid / Pursuit Lead | Bid Director | Commercial Lead | Bid Manager | Client debrief invitation, submitted proposal | Debrief notes, evaluator score card | Medium | Sequential
BM | BM-12 | Lessons learned & knowledge capture | MAPPED | Lessons report, content library updates, process improvement actions | Win / Loss Debrief | Playbook B10 | Conduct internal lessons learned review with full bid team | Bid Manager | Bid Director | All Leads | — | Debrief notes, bid programme, team feedback | Lessons learned report, improvement actions | Medium | Sequential
BM | BM-12 | Lessons learned & knowledge capture | MAPPED | Lessons report, content library updates, process improvement actions | Win / Loss Debrief | Playbook B10 | Update content library with new case studies, evidence and reusable content | Bid Coordinator | Bid Manager | SMEs | All | Lessons learned report, approved new content | Updated content library entries | Low | Sequential
BM | BM-13 | Bid risk & assumptions register | PARTIAL | Bid risk register (process risks, scheduling assumptions, resource risks) | Bid Process Risk Management | Implied across playbook | (No L3 tasks defined - needs authoring)
BM | BM-14 | Clarification submission & response management | MAPPED | Clarification response log with impact assessment | Clarification Management | Playbook B2 | Submit clarification questions within procurement deadlines and track responses | Bid Manager | Bid Director | All Workstream Leads | — | Approved Q list, procurement portal access | Submitted Qs, clarification response log | Low | Sequential
BM | BM-14 | [5 empty] | REVIEW NOTE: Moved from SAL-08 per point 3. Bid management activity, not sales capture.
BM | BM-15 | Clarification impact analysis & workstream updates | MAPPED | Updated requirements/assumptions across workstreams | Clarification Impact Assessment | Implied in Playbook B2/B7 | (No L3 tasks defined - needs authoring)
BM | BM-15 | [5 empty] | REVIEW NOTE: Moved from SAL-09 per point 3.
BM | BM-16 | Win strategy refresh (post-ITT) | NEW — PROPOSED | Updated win strategy, refreshed PWIN score | Win Strategy Refresh | Playbook B4 | Refresh and validate win strategy, PWIN score and competitive intelligence post-ITT receipt | Bid / Pursuit Lead | Bid Director | Capture Lead / Commercial | Bid Board | ITT/ITN, win strategy, PWIN score | Updated win strategy, refreshed PWIN score | High | Sequential
BM | BM-16 | Win strategy refresh (post-ITT) | NEW — PROPOSED | Updated win strategy, refreshed PWIN score | Win Strategy Refresh | Playbook B4 | Update stakeholder map and adjust client engagement plan post-ITT | Capture Lead / Account Manager | Bid Director | Bid Manager | — | Stakeholder map, ITT requirements | Updated stakeholder plan, revised engagement actions | Medium | Sequential
BM | BM-16 | [5 empty] | REVIEW NOTE: New activity from playbook B4 (Qualification). This is the formal re-check after ITT receipt: is the win strategy still valid? Has anything changed? Playbook gate: "Win Strategy Re-confirmation" (Bid Board).
GOV | GOV-01 | Pursuit approval (configurable) | MAPPED | Pursuit approval decision record | Pursuit Governance | Playbook G2/G5 | (No L3 tasks defined - needs authoring)
GOV | GOV-02 | Solution & strategy review (configurable) | MAPPED | Solution review decision record | Solution Governance | Playbook G7 (Storyboard Sign-off implied) | (No L3 tasks defined - needs authoring)
GOV | GOV-03 | Pricing & risk review (configurable) | MAPPED | Pricing decision record + approved price | Commercial Governance | Playbook G8/G9 (Commercial Risk Gate, Pricing Approval) | (No L3 tasks defined - needs authoring)
GOV | GOV-04 | Legal & contractual review (configurable) | NEW — PROPOSED | Legal review decision record | Legal Governance | Product gate G4 exists but no GOV activity to prepare for it | (No L3 tasks defined - needs authoring)
GOV | GOV-04 | [5 empty] | REVIEW NOTE: Per point 8: Product has gate G4 (Legal & Contractual Review) but no corresponding GOV activity. This new activity prepares for and delivers the legal governance review. Links to G4.
GOV | GOV-05 | Executive approval (configurable — may be multi-tier) | MAPPED | Executive approval decision record(s) | Executive Governance | Playbook G5/G11 | (No L3 tasks defined - needs authoring)
GOV | GOV-06 | Final submission authority (configurable) | MAPPED | Submission authority confirmation | Submission Authority | Playbook G12/G15 | (No L3 tasks defined - needs authoring)
PRD | PRD-01 | Compliance matrix & requirements mapping | MAPPED | Compliance matrix (live) | Compliance Checking | Playbook P1 | Perform detailed compliance check against all ITT/ITN requirements | Bid Manager | Bid Director | Legal / Commercial | Solution Owner | ITT/ITN documentation, compliance checklist template | Compliance matrix, mandatory requirements register | High | Sequential
PRD | PRD-02 | Section drafting & content assembly | MAPPED | Draft response sections | Draft Writing | Playbook P4 | Produce Executive Summary, Win Narrative, Key Themes | Senior Bid Writer | Bid / Pursuit Lead | Capture Lead / Commercial | Bid Manager | Writer briefs, storyboards, win themes | Executive summary draft, section drafts v0.1 | High | Parallel
PRD | PRD-02 | Section drafting & content assembly | MAPPED | Draft response sections | Draft Writing | Playbook P4 | Produce technical and solution section drafts across all lots/questions | Technical Bid Writer / SME | Technical Owner | Solution Architect | Bid Manager | RTM, solution design, writer briefs | Technical section drafts v0.1 | High | Parallel
PRD | PRD-02 | Section drafting & content assembly | MAPPED | Draft response sections | Draft Writing | Playbook P4 | Produce commercial and pricing schedules | Commercial Lead | Bid Director | Finance | Legal | Approved pricing mandate, T&C redline | Pricing schedules, commercial response drafts | High | Sequential
PRD | PRD-03 | Evidence, case studies & CV assembly | MAPPED | Evidence pack | Content Library Management | Playbook P5 (shared with SOL-10) | (No L3 tasks defined - needs authoring)
PRD | PRD-04 | Pricing schedules & commercial response | PARTIAL | Pricing response documents | Commercial Response Production | Playbook P4 (third writing task) | (No L3 tasks defined - needs authoring)
PRD | PRD-05 | Pink review (storyboard/outline) | MAPPED | Pink review scorecard & actions | Pink Team Review (30–50% draft) | Playbook P6 | Conduct Pink Team review against evaluation criteria; assess win theme penetration | Independent Reviewer | Bid Director | Capture Lead / Commercial | All Writers | Section drafts v0.1, evaluation criteria, win themes | Pink Team review report, action log | High | Sequential
PRD | PRD-06 | Red review (full draft) | MAPPED | Red review scorecard & actions resolved | Red Team Review (80–90% draft) | Playbook P6 | Conduct Red Team review — evaluator simulation against scoring criteria | Senior Independent Panel | Bid Director | Solution Owner / Commercial | Bid Manager | Near-final drafts, evaluation model | Red Team scores, gap analysis, priority actions | High | Sequential
PRD | PRD-07 | Gold review (final/executive) | MAPPED | Gold review scorecard & sign-off | Gold Team Review (Final) | Playbook P6 | Final executive quality review; confirm compliance, completeness and tone | Bid Board (Partner level) | Senior Responsible Exec | Commercial / Legal | Bid Manager | Final draft proposal | Gold Team sign-off, approved final document | High | Sequential
PRD | PRD-08 | Final QA & formatting | MAPPED | QA checklist complete | Document Production & Formatting | Playbook P7 | Apply corporate template, branding, page limits and formatting requirements | Bid Coordinator / DTP | Bid Manager | Brand/Design | Bid Director | Approved final content, ITT formatting requirements | Formatted proposal document(s) | Medium | Sequential
PRD | PRD-08 | Final QA & formatting | MAPPED | QA checklist complete | Document Production & Formatting | Playbook P7 | Proof-read, spell-check, and cross-reference all sections | Bid Coordinator | Bid Manager | Senior Bid Writer | — | Formatted document | Proof-read final document, error log cleared | Medium | Sequential
PRD | PRD-09 | Submission packaging & upload | MAPPED | Submission confirmation receipt | Final Submission | Playbook P7 + B5 | Conduct final compliance check against all mandatory requirements before submission | Bid Manager | Bid Director | Legal / Commercial | — | Compliance matrix, final formatted document | Compliance sign-off sheet | High | Sequential
PRD | PRD-09 | Submission packaging & upload | MAPPED | Submission confirmation receipt | Final Submission | Playbook P7 + B5 | Execute submission plan: upload, portal submission, confirmation receipt | Bid Manager | Bid Director | IT Support | Commercial Lead | Gold-approved documents, submission portal credentials | Submission confirmation, submitted documents archive | High | Sequential
POST | POST-01 | Presentation design & development | MAPPED | Presentation deck, speaker notes, narrative | Presentation Preparation | Playbook B6 | Design and develop bid presentation (slides, narrative, evidence, demos) | Bid / Pursuit Lead | Bid Director | Solution Owner / Commercial | Bid Manager | Submitted proposal, evaluation feedback, win themes | Presentation deck, speaker notes, rehearsal plan | High | Sequential
POST | POST-02 | Presentation rehearsals & coaching | MAPPED | Rehearsal debrief notes, revised deck, Q&A prep | Rehearsal & Coaching | Playbook B6 | Conduct structured presentation rehearsals and coaching (Boardroom Simulator) | Bid / Pursuit Lead | Senior Responsible Exec | SME / Commercial | Bid Manager | Presentation deck, evaluator model, coaching plan | Rehearsal debrief notes, revised deck | High | Iterative
POST | POST-03 | Presentation delivery | MAPPED | Presentation delivered, Q&A record | Presentation Delivery | Playbook B6 | Deliver bid presentation to evaluation panel; manage Q&A | Bid Director / Senior Exec | Senior Responsible Exec | Commercial / Technical | Bid Manager | Approved presentation, rehearsal outcomes | Presentation delivered, Q&A record | High | Sequential
POST | POST-04 | Post-submission clarification management | MAPPED | Clarification log, submitted responses, updated risk log | Post-Submission Clarification Management | Playbook B7 | Receive, log and triage all post-submission clarification requests from client | Bid Manager | Bid Director | All Workstream Leads | Commercial Lead | Client clarification requests | Clarification log, triage register | Medium | Iterative
POST | POST-04 | Post-submission clarification management | MAPPED | Clarification log, submitted responses, updated risk log | Post-Submission Clarification Management | Playbook B7 | Draft, review and submit clarification responses within deadlines | Technical Owner / Commercial | Bid Director | Legal / SME | Bid Manager | Clarification log, approved response process | Submitted clarification responses, updated risk log | High | Iterative
POST | POST-05 | BAFO preparation & revised pricing | PARTIAL | Revised pricing model, updated solution elements | BAFO Preparation | Partially in Playbook B8 | (No L3 tasks defined - needs authoring)
POST | POST-06 | BAFO governance approval | MAPPED | Board-approved BAFO mandate | BAFO Governance | Playbook B8 (Commercial Escalation Gate) | Obtain internal approval for any material changes to commercial position | Commercial Lead | Partner / Senior Responsible Exec | Legal / Finance | Bid Director | Negotiation notes, proposed changes | Board-approved commercial mandate update | High | Sequential
POST | POST-07 | Contract negotiation support | MAPPED | Negotiated T&C schedule, agreed pricing | Commercial & Contract Negotiation | Playbook B8 | Lead commercial and T&C negotiations with client procurement team | Commercial Lead | Bid Director | Legal / Senior Exec | Finance | Preferred bidder notification, client T&Cs, commercial model | Negotiated T&C schedule, agreed pricing | High | Iterative
POST | POST-08 | Award processing & mobilisation handover | MAPPED | Handover pack, delivery team briefed, PID | Award & Mobilisation Preparation | Playbook B9 | Receive and process contract award; initiate formal mobilisation workstream | Bid Manager / Programme Director | Senior Responsible Exec | Commercial / Legal | All Leads | Award letter, signed contract | Mobilisation plan v1, project initiation document | High | Sequential
POST | POST-08 | Award processing & mobilisation handover | MAPPED | Handover pack, delivery team briefed, PID | Award & Mobilisation Preparation | Playbook B9 | Conduct post-award knowledge transfer to delivery team | Bid Manager | Bid Director | Delivery Director | Programme Manager | Bid file, commercial model, risk register, RTM | Handover pack, delivery team briefed | High | Sequential
POST | POST-08 | [5 empty] | REVIEW NOTE: Gate Summary Direct matches: 6 of 19 playbook gates have clear product equivalents. Partial matches: 5 gates are partially covered (folded into broader product gates or handled as activities). No match: 8 gates have no product equivalent. Most should become milestones under the renamed "Key Milestones" view (per point 7). Key architectural insight: The playbook has more gates because it treats every quality checkpoint as a gate. The product distinguishes between governance gates (formal approval, configurable, with entry criteria) and milestones (events that happen when activities complete). Per point 7, the product should show both — governance gates AND programme milestones — under a unified "Key Milestones" view. Summary Statistics 83 Proposed Activity Count

## Gaps & Extensions
Type | Title | Description | Suggested Action | YOUR REVIEW: Accept? (Y/N) | YOUR REVIEW: Comments
MISSING | RFI Response Management (2 L3 tasks) | Playbook has a formal RFI stage with response planning and drafting. Product assumes ITT/RFP as the starting point. | Recommendation: Consider adding as optional/configurable stage. Some procurement routes start with PQQ/RFI before ITT. Could be a BM activity that's deactivated by default.
MISSING | Procurement timeline mapping and milestone planning (1 L3 task) | Playbook B2 includes "Map procurement timeline, evaluation stages, and decision milestones." Product captures this in bid setup wizard (submission deadline, procurement route) but doesn't have an explicit activity for mapping the full procurement process. | Recommendation: Fold into BM-01 (Kickoff) or BM-02 (BMP) as an L3 task. The procurement timeline mapping is part of kick-off, not a separate activity.
MISSING | Resource mobilisation as a formal checkpoint (2 L3 tasks + gate) | Playbook has B3 with a "Resource Mobilisation Gate" — full team confirmed, clearances initiated, partners signed. Product has BM-04 (resource tracking) but it's continuous (dur:0), not a gated milestone. | Recommendation: Per your review — add Resource Mobilisation as a formal milestone. Consider splitting BM-04 into initial mobilisation (gated) and ongoing tracking (continuous).
MISSING | Formal re-qualification after ITT receipt (2 L3 tasks + gate) | Playbook B4 has "Win Strategy Re-confirmation" gate — is the win strategy still valid after seeing the full ITT? Product doesn't have this checkpoint. | Recommendation: Proposed as BM-16 in the mapping above. Includes "Bid Board Win Strategy Re-confirmation" gate. Important for large bids where ITT may reveal surprises.
MISSING | Content library retrieval, adaptation, and gap-filling (2 L3 tasks) | Playbook has P5 as a separate L1 stage. Product distributes this across SOL-10 (evidence strategy) and PRD-03 (evidence assembly). | Recommendation: No new activity needed. Product's split (SOL-10 = strategy, PRD-03 = assembly) is the right decomposition. L3 tasks from playbook P5 are already mapped to those activities.
MISSING | Re-bid planning 18–24 months before contract expiry (1 L3 task) | Playbook has B11 as a cycle-restart activity. As you noted — this is the same as "what's our win strategy" whether new or re-bid. | Recommendation: No separate activity needed. The re-bid context is handled by SAL-02 (incumbent review, configurable) and the bid setup wizard's incumbency flag. B11 is the trigger to restart the cycle, not a bid-level activity.
MISSING | Client-driven procurement timeline events | Playbook B2 captures procurement milestones (ITT release, clarification deadline, site visits, evaluation stages). Product has submission deadline but no formal procurement milestone timeline. | Recommendation: Per point 7 — rename "Governance Gates" to "Key Milestones" with two groups: (1) Procurement milestones (client-driven, from bid setup), (2) Programme milestones (internally driven, from activity completion).
EXTENSION | PRODUCT EXTENSION — SOL-08: Innovation & continuous improvement | Not in playbook. Critical for UK government bids where innovation is a scored criterion. Retain — needs L3 authoring.
EXTENSION | PRODUCT EXTENSION — SOL-09: Social value proposition | Not in playbook. Mandatory scoring component in UK public sector (PPN 06/20, 10% minimum weighting). Retain — needs L3 authoring.
EXTENSION | PRODUCT EXTENSION — SOL-05: Technology & digital approach | Not separated in playbook (folded into P3 solution architecture). Product correctly separates it for technology-heavy contracts. Retain.
EXTENSION | PRODUCT EXTENSION — LEG-03: Insurance & liability review | Not in playbook as separate activity. Essential for large government contracts — PI, PL, EL, cyber insurance. Retain.
EXTENSION | PRODUCT EXTENSION — LEG-05: Data protection & security review | Not in playbook (only security clearance vetting in B3). Critical for defence/justice contracts. DPIA, security classification, data handling. Retain.
EXTENSION | PRODUCT EXTENSION — DEL-03: Performance framework & KPIs/SLAs | Not in playbook. Essential for service contracts — SLA design underpins delivery model and commercial model. Retain.
EXTENSION | PRODUCT EXTENSION — DEL-05: Business continuity & exit planning | Not in playbook. Required in most government contracts — BC/DR plans, exit/handback provisions. Retain.
EXTENSION | PRODUCT EXTENSION — BM-09: Competitive dialogue management | Not in playbook. Procurement route specific (CD, CPN). Correctly configurable (dur:0, activatable). Retain.
EXTENSION | PRODUCT EXTENSION — SUP-02 through SUP-06 | Playbook has 2 L3 tasks for partner assessment (C3). Product has 6 supply chain activities with much more granularity. Correct for large outsourcing/defence contracts with complex supply chains. Retain.

## Gate Comparison
Playbook Gate | Phase | Product Gate | Match | Notes | YOUR REVIEW: Accept? (Y/N) | YOUR REVIEW: Comments
G1 Opportunity Screening | Capture | — | No match | Pre-bid screening. Product starts at ITT receipt. Consider as procurement milestone.
G2 Formal Pursue Decision (DQC) | Capture | G1 Pursuit Approval | Match | Same concept. Product G1 = Playbook G2/G5.
G3 Buyer Values Sign-off | Capture | — | No match | Capture-phase gate. Not in product. Consider as milestone linked to SAL-01 completion.
G4 Win Strategy Gate | Capture | — | Partial | Subsumed into SAL-06 methodology gate (win strategy lock).
G5 Bid Board Mandate Approval | Capture | G1 Pursuit Approval | Match | Product G1 combines playbook G2 + G5.
G6 Programme Baseline Gate | Proposal | — | No match | Bid programme baselined. Consider as milestone linked to BM-01 completion.
G7 Storyboard Sign-off | Proposal | G8 Storyboard Sign-off | Match | Direct match. Per point 1: rename to "Pink Review Complete".
G8 Commercial Risk Gate | Proposal | G3 Commercial/Finance | Match | Direct match.
G9 Pink Team Gate | Proposal | — | Partial | Product has PRD-05 as activity but no separate gate. Pink review IS the storyboard sign-off (G8/G7).
G10 Red Team Gate | Proposal | — | Partial | Product has PRD-06 as activity. Consider adding as milestone — "Red Review Complete".
G11 Gold Sign-off Gate | Proposal | G9 Final Submission Authority | Partial | Product G9 is broader (gold + exec approval + QA). Consider separating gold complete as milestone.
G12 Final Compliance Gate | Proposal | G9 Final Submission Authority | Partial | Folded into product G9.
G13 Resource Mobilisation Gate | B&P | — | No match | Per your review — should be added as milestone.
G14 Win Strategy Re-confirmation | B&P | — | No match | Proposed as part of BM-16. Consider as milestone.
G15 Submission Confirmation | B&P | G9 Final Submission Authority | Match | Part of product G9.
G16 Rehearsal Sign-off | B&P | — | No match | Presentation readiness. Consider as milestone linked to POST-02.
G17 Commercial Escalation Gate | B&P | G10 BAFO Authority | Match | Direct match.
G18 Contract Award — Transition | B&P | — | No match | Post-award transition gate. Consider as milestone linked to POST-08.
G19 Re-bid Decision Gate | B&P | — | No match | Cycle restart. Out of product scope (pre-bid decision).

## Instructions
PWIN Methodology Mapping Review — How To Use This Workbook
This workbook is extracted from methodology_mapping_review.html for your line-by-line review.
SHEET 1: L3 Task Review
- Each row is one L3 task (the actual activity someone performs)
- Columns A-P are the current proposed content — read but do not edit these
- Column Q (Accept?): Enter Y to accept, N to reject, or M to modify
- Column R (Comments/Changes): Write your changes, corrections, or new task descriptions here
- Yellow rows with "REVIEW NOTE:" are questions or flags for your attention — respond in Column R
- Rows saying "(No L3 tasks defined)" need you to write the tasks in Column R
SHEET 2: Gaps & Extensions
- Playbook content missing from the product, or product content not in the playbook
- Column E (Accept?): Y to include, N to exclude
- Column F (Comments): Any changes or reasoning
COLUMN DEFINITIONS:
Workstream — The workstream code (SAL, SOL, COM, etc.)
Activity Code — Unique ID for the L1 activity (e.g. SAL-01)
Activity Name — What the activity is called
Mapping Status — MAPPED / PARTIAL / PRODUCT ONLY / NEW
Activity Output — The primary deliverable of the whole activity
L2 Sub-Process — The grouping within the activity
Playbook Ref — Which playbook section this maps to
L3 Task — The specific task an individual performs (this is what you are reviewing)
R (Responsible) — Who does the work
A (Accountable) — Who approves / is ultimately answerable
C (Consulted) — Who provides input before the task
I (Informed) — Who is told after the task
Inputs — What you need before you can start this task (pre-requisites, source documents)
Outputs — What this task produces (named deliverable / artifact)
Effort — Relative effort: Low / Medium / High
Type — Execution pattern: Sequential / Parallel / Iterative
TIPS:
- Use Excel filters on Column A (Workstream) to review one workstream at a time
- Use Column D (Mapping Status) filter to focus on PRODUCT ONLY or NEW items first
- If you want to add entirely new L3 tasks, add new rows below the relevant activity
- If you want to reorder tasks, note the desired order in the Comments column
- Save as .xlsx and upload back — Claude will parse your review columns automatically